## API updates
API updates
4.13
Dojo
Swipe widget
Bookmark editing
4.12
AbortSignal
Slider widgets

## to do
priority | Assigned to | Completed? | Task | files | functions | vars | Comments
|  | y | zoom to drawn rectangle
| TS | TS | better looking video speed tool | VideoPanelWidget.js, youtube.js |  | speedHTML
| TS | TS | tooltips for video/photo controls
low | T |  | prettier playback controls?
| TS | JN | adjust video & photo sizes to fit entire image in panel | VideoPanelWidget.js, PhotoPlaybackWidget | processPicasaData() |  | resize of video remaining Still need to get BorderContainer splitter event
| TS | TS | photo panel: Message at bottom indicating that photo controls are disabled because photo display is linked to video, and to disable linking and display photo controls, click the link icon in video panel.
|  | y | when sorted on a column, mouseover on a row still brings up the same popup
| JN | y | Generalize QueryBasedTablePanelWidget, so not specific to SZ Units
|  | y | disable requery of points on panel resize? Refresh button, turns red when panel resizes?
|  | p | and on point/unit popup |  |  |  | JN: I think the API now adjusts positioning of popups so they don't force an extent change
| JN | y | SZ Units table: Automatically hide table columns with no data by default
|  | p | graphics layers: no display until mouseover |  |  |  | Steve request. Instead, JN made them smaller, so you can still see which points are selected when not using autoRefresh
|  | y | handle too many photo points: filter every other? User option? |  |  |  | Graphics objects are now limited minimal pixel spacing, set in website settings panel
low | JN |  | minimal pixel distance for video points, like for photos? |  |  |  | Useful now that points can be queried at greater extents
low | JN |  | check Python code for remaining ArcGIS functions |  |  |  | Steve request
|  | p | previous extent button (use Bookmarks widget?)
| TS | JN | video speed slider: get text indicator to show speed (e.g. "2X") instead of percent |  |  |  | basically there -- update where "playbackRate" appears
| JN | y | Add links to REST services for SZ, FA, SS
low | TS |  | semi-transparent background for text over imagery, so it's more visible
| TS | y | tooltips for lock & link buttons
|  | y | Settings panel
| JN | y | Hide SZ stuff when in FA tab, and vice-versa
| JN | p | Things don't work if you start zooming before initial draw of SZ video lines |  |  |  | works okay on server?
| TS | JN | Better default column widths for SZ Unit tables | mapStuffWidget.js |  | szUnitsWidget | First, temporarily comment out this line in QueryBasedTablePanelWidget.js: col.hidden = (nonNullCount[col.field]===0); Then visually inspect, and where necessary, set so column labels fit. This is done by adding width info for columns to the specialFormatting property. (Leave the CMECS fields unchanged, and don't do anything with labels of 3-4 characters.)
|  | p | Bug: Adding TextSymbol to Locales causes problems | QueryBasedPanelWidget | makeClickableGraphics | textOverlayPars property in faWidget | put TextSymbols in separate layer
| JN | y | get mouseover of graphic object to highlight row in table | QueryBasedPanelWidget.js | displayPlayButton |  | Because I'm currently using OnDemandGrid, only partial set of rows are present at any on time | dGrid Selection module API
| JN | y | 2 queries when click on "go to subarea"?
| JN | y | Leave dropdown selection out of query where clause when dropdown is not visible
low |  |  | Locale marker background transparency |  |  |  | textOverlayPars
|  | y | saved extents
| TS? | JN | start on Shore Stations add-on | mapStuffWidget.js |  | ssWidget | Copy parameters for faWidget into ssWidget, modify for SS
| JN | p | Deal with Picasa deprecation | Use AOOS service? |  |  | The Picasa API is deprecated. See https://developers.google.com/picasa-web/ for more details and the migration guide.
|  | p | Deal with "more videos" on YouTube video pause |  |  |  | YouTube API no longer allows disabling showing of "more videos" when video is paused
low |  |  | FA/Sites tab: Choose locale from different region: Flex: no DD for Regions, so it works fine JS: need to either ignore Region DD selection, or limit Locale options to current Region
| TS | JN | LayerList widget: Less space between items in list |  |  |  | CSS settings?
|  | p | set correct initial photo size for photos from Axiom |  |  |  | not using Axiom anymore, so moot point
|  | y | FA & SS panel_Enabled: Hide when not in correct area tab
|  | y | coordinate SZ video/photo point generation with layer visibility in LayerList
low |  |  | Add Locales tab to Shore Stations?
|  | p | formatting of FA & SS table columns |  |  |  | new SZ fields not done yet
|  | y | update layout pics in splash page
|  | JN | Site/Station zoom to some specific scale
regions table sometimes disappears when going back from subareas tab
|  | ? | remove "search result" popup on using locator
|  | y | show/hide Video Flightline legend
low |  |  | smaller popups
track widths of cell contents for each column, and use to set column width
|  | y | compress SS photos
|  | p | get highres verson of photo on right-click:download |  |  |  | Still can't get it to download straight to file file rather than open in new tab.
bring up to 10.14 (and make bookmarks work under this)
|  | JN | checkbox for global/inView on searchWidget |  |  |  | put widget inside DIV, add checkbox at bottom of DIV?
|  | p | hide LayerList when in FA/SS? |  |  |  | keep track of user state, so stays off in SZ mode when user has turned off?
|  | JN | change "eye" checkbox in LayerList to regular box?
compare speeds of services on NOAA & PSMFC servers
go to locale/site from popup
X