## FA bugs
FA Bugs | Priority | Done?
Highlight Sites on mouseover: bigger, RGB 74, 241, 242 |  | y?
Cancel button for Species dropdown panel | n
If a species is currently selected and SP panel is opened again, "Close" button has changed to "Go". Still works to close panel, though.
Put graphic object ID in hidden column? | n
Eventually get the dropdowns to respond to spatial filter as well? |  | y
"Scientific name" radio button in Species dropdown doesn't work |  | y
Finish setting download headers | y | y
selection box issues -- box showing/not showing at inappropriate times | y | y
Prepare links for switching between SZ/FA/SS |  | y
Checking FMP checkbox filters the table on FMP=1 |  | y
Selection of "All" or "FMP" shows up in button text |  | y
The 2 "Show Popups" boxes work differently |  | y | renamed header "Show Popups" to "Show Layer"
Put "Species" label next to SP selection button |  | y
Changes to raw download csv fieldnames: change WebSiteLocation display to Location, move RawSite immediately after SiteID, add RawEvent immediately after EventID |  | y
Add all 5 FMP fields to raw download list |  | y
Popups docked by default |  | y
Change messages from red font color to black (e.g., "Download in progress….." message in download window, "Looking for photo points" and "Site photos can be seen….." messages in photo panel, and "Looking for sites" message in table panel. |  | y
In advance of adding a ShoreStation-like species filter into Fish Atlas, would it be easy to add a search field in the window so that if you want data on capelin you can simply type in capelin rather than having to scroll through the list to find it? Also, might said search tool be able to find walleye pollock if someone were to search for just the word pollock? Likewise, might the search tool be able to bring up both Arctic and Pacific sand lance with a search for sandlance or sand lance? In the event this would be a lot of work, please advise on a timeline for the implementation of a ShoreStation-like species filter |  | pending approval
Think about more generic browser tab name, to cover SZ, FA & SS. Maybe "ShoreZone, Fish Atlas & Shore Stations"? |  | y
FMP filter option not working | y | y
need field name in vw_FishCounts_flat
Also, waiting on new list, possibly with different field name
Regarding the download window, please change the title to Data download, increase the length of the filename area, and add the word Raw to the beginning of the filename when raw is selected. | n | y
The header on the Fish Catch table currently includes SiteID and WebLocation. It would be great to have Region in there, right below SiteID. | n | y
When you click the magnifying glass in the Sites table, the map zooms in to 200m, which doesn't provide much in the way of orientation. I'm thinking 1km might be better. Thoughts? BTW, the scale bar at zoom-in shows 0.2 km in GOA, Aleutians, and Bering - and 200 m in Chukchi and Beaufort. I have no worries about the units; just an FYI. :) | n | y
Photos not coming up | y | y
change the word Hauls to Sets in the Regions table, Sites table, and Sites popup |  | y
Pad SiteID values so they sort correctly | y | y
Update download list (see Word doc) | y | y
I just discovered that while Items and Catch tallies update in response to the sites that are selected, the Hauls and Species tallies don't change. | y | y
File name should be "Fish Catch for Alaska"?
Note on A62: HACK in MakeTable (line 439)

## Sue Saupe concerns
allow units to display at greater extents?
nautical charts, bathymetry?
rendering of Habitat, etc. | Steve will do?

## Sheet2
post-meeting
3D Units
initial zoom tilted so sky not visible?
modify 3D extent function to handle when sky is visible
message to zoom in when not getting all features
help on map navigation?
groupdataextract available at .5 or 1X scale of Chichagof
when sorted on a column, mouseover on a row still brings up the same popup
fix formatting of unit table
message for download failure
back-up to previous dialog
photo marker skips through when there is a discontinuity
Dutch Harbor issue
not there any more?
(figure out multiple copies of unit graphic objects)
try to get 3D version? (maybe not that high-priority)
[query layers and alternate layout are not high-priority]
Add checkbox to turn unit display on/off, default to off
prevent panning when highlighting graphic object that extends beyound current view
only create graphics that are entirely within view?
use polylines (instead of unit envelopes) to display units (maybe line for selected, envelope for background)
lighter envelope background
degree symbols in photo/video headers
tooltips for unit field values
4.5 version loses line breaks in map popups
Unit query failure -- was due to missing rendering for a layer
get CMECS on site
darker/bolder fonts
smaller video point graphics
NOAA colors
hide middle panel
add tab for 3D Units site
unit table not always showing all fields
download: add video clips
hide graphic selection marker when zoomed out, or when "show unit markers" is turned off
consistent order of unit table columns

## layers show issue
bug: | layers=show:-1 | 4.3
| layers=show:3 | 4.5

## Sheet1
identify areas that could be debugged by Tristan?
try site on 1and1.com with iPad
offline app
GP service: storage estimate
make panel for OfflineApp widget, with more info & choices
CSS: Use "em" or "rem" instead of "px" for units, to scale with device size
or just use minimum size? (24px?)

## Devices
Browser:
Device | Chrome | Safari | FireFox | IE | Edge
Windows desktop
Windows laptop
Macbook Pro
iPad Mini
Xoom tablet
iPod Touch
OfflineLink widget is messing up iOS
with OfflineLink disabled, video queuing/playback is still not working

## questions
Questions for Steve:
Does PSMFC server have streaming video yet?
(and photos)

## API wish list
ArcGIS JavaScript API 4.x wishlist
esri/views/MapView |  | get mouse pointer to point correctly
position indicated by pointer is maybe 10 pixels SE of actual point?
(or else hitTest is inaccurate)
| hitTest method | What is search tolerance?
Can this be set/read?
esri/widgets/LayerList |  | start expanded? (check first)
esri/widgets/Locate |  | add parameter to set the scale to zoom to
esri/widgets/Popup |  | prevent popup from changing map extent | There is a reposition() function, but have to figure out how to respond to Popup "show" event
shift popup box position as needed to fit within the map frame, rather than panning to fit the box